Pop-Up Restaurant Template

A. Core Concept & Brand Narrative

- Pop-Up Name: [e.g., "The Midnight Noodle Co." or "Chef [Name]'s Secret Supper"]

- Concept & Culinary Theme:

  - *(e.g., 90s Nostalgia Dinner Party, 10-Course Vegan Tasting, Underground Izakaya)*

- Mission & "Why Pop-Up":

  - (e.g., "To test a future brick-and-mortar concept," "To celebrate a seasonal ingredient," "To create an exclusive, one-of-a-kind dining experience.")

- Target Audience:

  - (e.g., Food Adventurers, Local Influencers, Fine Dining Enthusiasts, Followers of the Chef)

- Price Point & Model:

  - (e.g., $$$ - Prix Fixe Ticketed, $$ - A la Cart Pop-Up, $$$$ - Charity Gala)

- Unique Selling Proposition (USP):

  - *(The core of the pop-up. e.g., "A 5-course dinner served in a secret rooftop garden," "The first local showcase of a specific regional cuisine," "An immersive theatrical dining experience.")*

B. Venue Strategy & Negotiation

1. Venue Selection Criteria

| Venue Type | Pros | Cons | Key Considerations |
| --- | --- | --- | --- |
| Existing Restaurant (Dark Kitchen/Night) | Full kitchen, permits, seating | Limited to off-hours, may have rules | Negotiate a flat fee or percentage of sales. |
| Unconventional Space (Gallery, Loft, Studio) | Unique ambiance, high "wow" factor | May lack infrastructure (kitchen, HVAC) | Check zoning and health department rules for temporary events. |
| Brewery/Distillery/Winery | Built-in audience, liquor license | May have food truck partnerships already | Propose a collaborative menu pairing. |
| Outdoor/Public Space (Park, Rooftop) | Scenic, high demand | Weather-dependent, complex permits | Always have a solid weather contingency plan. |

- Non-Negotiable Checklist:

  - Health Department Compliance for temporary food service

  - Adequate Power (for cooking equipment)

  - Ventilation (or ability to bring it in)

  - Access to Water & Gray Water Disposal

  - Adequate Restrooms for guests

  - Liability Insurance requirements

2. Venue Negotiation Guide

- Offer Value: Propose a win-win (e.g., "We'll handle all marketing and bring our followers to your space on a slow night.").

- Compensation Models:

  - Flat Fee: You pay the venue $[Amount] for the night. You keep all revenue.

  - Percentage of Sales: You give the venue [e.g., 15-30%] of gross food & beverage sales.

  - Hybrid Model: Lower flat fee ($[Amount]) + smaller percentage ([e.g., 10%]).

- Key Contract Clauses:

  - Term: Clearly define dates/times for load-in, service, and breakdown.

  - Liability & Insurance: Specify who holds what insurance. You will likely need a one-day event policy.

  - Cancellation Policy: Terms for both parties.

  - Profit Split: Clearly state how and when the venue gets paid.

C. Timeline for a Temporary Operation

*(Example for a 4-week pop-up series)*

- T-12 Weeks: Concept & Planning

  - Finalize concept, menu, and budget.

  - Begin scouting and negotiating with venues.

- T-8 Weeks: Venue & Legal

  - Sign venue contract.

  - Secure one-day event insurance.

  - Apply for any necessary temporary food permits.

- T-6 Weeks: Marketing & Pre-Sales

  - Launch social media accounts and website/landing page.

  - Announce dates and release ticket/pre-sale link.

  - Begin influencer/PR outreach.

- T-2 Weeks: Operations Finalization

  - Finalize staff (hire if necessary).

  - Place final orders with food suppliers.

  - Confirm equipment rental order.

- T-1 Week: The Final Push

  - Final menu run-through and staff briefing.

  - Post daily "sneak peek" content on social media.

  - Send reminder email to ticket holders.

- Pop-Up Week: Execution

  - Load-in and setup.

  - Execute Service.

  - Breakdown and load-out.

- T+1 Week: Post-Mortem & Follow-Up

  - Send thank-you emails to guests and staff.

  - Analyze financial and customer feedback.

  - Plan next steps (new series? brick-and-mortar?).

D. Equipment Sourcing: Rent vs. Buy Analysis

| Equipment | Rent (Good for...) | Buy (Good for...) | Decision Matrix |
| --- | --- | --- | --- |
| Major Cooking (Range, Oven) | One-off events; no storage | Long pop-up series; future use | Rent if: Single event. Buy if: 10+ events planned. |
| Refrigeration (Low-Boy, Freezer) | Any event without on-site units | A long-term pop-up project | Almost always Rent for convenience. |
| Smallwares (Pans, Utensils) | Filling gaps in your kit | Building a permanent kit | Buy basics, rent specialty items. |
| Service Items (Plates, Glassware) | Themed events; no dishwasher | Consistent branding; many events | Rent for elegance and ease. Buy compostable for casual. |
| POS System | Any event | A long series or permanent move | Rent/Use Mobile POS (Square, Toast Go). |

- Total Rental Cost Estimate: $[Amount] per event.

- Total Purchase Cost Estimate: $[Amount] (one-time).

E. Social Media & Marketing Strategy

1. Phased Marketing Rollout

- Phase 1: The Tease (T-6 Weeks)

  - Action: Create Instagram/TikTok account. Post cryptic, high-quality visuals (ingredients, mood boards, chef prepping) without revealing the full concept.

  - Goal: Build curiosity and initial followers.

- Phase 2: The Reveal (T-4 Weeks)

  - Action: Announce the pop-up name, dates, and venue. Launch a simple landing page for an email list.

  - Goal: Drive email sign-ups and concrete interest.

- Phase 3: The Launch (T-2 Weeks)

  - Action: Release the menu and open ticket sales/registrations. Collaborate with local food influencers for "takeovers" or giveaways.

  - Goal: Sell out the event.

- Phase 4: The Hype (T-1 Week)

  - Action: Post "behind-the-scenes" stories of prep, introduce the team, share countdowns.

  - Goal: Maintain excitement and minimize no-shows.

- Phase 5: The Experience (Event Week)

  - Action: Encourage guests to share their experience with a dedicated hashtag (e.g., #MidnightNoodleCo). Reshare user-generated content.

  - Goal: Create social proof and FOMO (Fear Of Missing Out) for the next event.

F. Path to Permanence Planning

1. Success Metrics for a Permanent Move

- Financial Viability:

  - Consistent sell-out of [e.g., 80%] of seats across [e.g., 10+] events.

  - Average customer spend of >$[Amount].

  - Positive net profit after all costs.

- Customer Demand:

  - Waitlist consistently [e.g., 2x] the number of available seats.

  - Strong, positive reviews on social media and Google.

  - Growing, engaged email list (>[e.g., 1,000] subscribers).

- Operational Execution:

  - Smooth service with minimal operational hiccups.

  - Proven, reliable team in place.

  - Streamlined supply chain and vendor relationships.

2. Steps to Brick-and-Mortar

- Validate Concept: Use pop-up revenue and customer data to secure investors or loans.

- Develop Business Plan: Create a full plan based on pop-up learnings (use the Full-Service Restaurant Template).

- Secure Funding: Use pop-up success stories (media clips, financials) in your pitch.

- Location Scouting: Leverage the community you built to find the perfect permanent home.

G. Critical Path to Pop-Up Launch

- Phase 1: The Big Idea (Complete this template)

- Phase 2: Venue & Legal

  - Secure Venue & Sign Contract

  - Obtain Temporary Food Permit & Event Insurance

- Phase 3: Financials & Marketing

  - Create Detailed Budget & Set Ticket Prices

  - Build Social Media Presence & Launch Marketing Phases

  - Open Ticket Sales/Reservations

- Phase 4: Operations & Sourcing

  - Finalize Menu & Source Suppliers

  - Hire & Brief Staff (Chefs, Servers)

  - Place Equipment Rental Order

- Phase 5: Execution

  - Conduct Soft Opening for Friends/Media

  - Execute the Pop-Up Event(s)

  - Gather Feedback & Analyze Performance